## TestPlan
Test plan
Click here to see the Test Plan

## MindMap
Mind Map For demo.nopcommerce.com | Link

## TestCase
Product Name |  | Nopcommerce | TC Start Date | 14/10/2025 | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | User Account Management (covers Registration, Login, Password Recovery) | TC End Date | 14/10/2025 | TC Execution End Date | - - |  |  |  |  | PASS | 20
Epic |  |  | Test Case Developed By | A.B.M. Mahmudul Hasan(Soumik) | Browser (tested) | Yes |  |  |  |  | FAIL | 5
Developer Name (TL) |  |  | Test Case Reviewed By | MD. Rubel | Performance (tested) | Yes |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 25
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Registration | Functional | Gender Field | Verify registration when Gender not selected | Registration should still work (Gender optional) | Registration completed successfully | Gender: Not selected | 1. Go to https://demo.nopcommerce.com/ 2. Click Register 3. Do not select Gender 4. Fill all other fields correctly 5. Click Register |  |  | Passed
2 | Registration | Functional | First Name Field | Verify registration when First Name field is empty | Error message “First name is required” should appear | Error message displayed: “First name is required” | First Name: Blank | 1. Go to https://demo.nopcommerce.com/ 2. Click Register 3. Leave First Name blank 4. Fill other fields correctly 5. Click Register |  |  | Passed
3 | Registration | Functional | First Name Format Validation | Verify registration when First Name contains invalid characters | Show error message “Wrong first name format” or first name field validation should prevent invalid characters | Accepts invalid input and registration completes successfully | First Name: Soumik@123 | 1. Go to https://demo.nopcommerce.com/ 2. Click Register 3. Enter Soumik@123 in First Name field 4. Fill all other fields correctly 5. Click Register | Click here to see the error. |  | Failed
4 | Registration | Functional | Last Name Field | Verify registration when Last Name field is empty | Error message “Last name is required” should appear | Error message displayed: “Last name is required” | Last Name: Blank | 1. Go to https://demo.nopcommerce.com/ 2. Click Register 3. Leave Last Name blank 4. Fill other fields correctly 5. Click Register |  |  | Passed
5 | Registration | Functional | Last Name Format Validation | Verify registration when Last Name contains invalid characters | Show error message “Wrong last name format” or last name field validation should prevent invalid characters | Accepts invalid input and registration completes successfully | Last Name:@@@ | 1. Go to https://demo.nopcommerce.com/ 2. Click Register 3. Enter @@@ in Last Name field 4. Fill other fields correctly 5. Click Register | Click here to see the error |  | Failed
6 | Registration | Functional | Email Field | Verify registration when Email field is empty | Error message “Email is required” should appear | Error message displayed: “Email is required” | Email: Blank | 1. Go to https://demo.nopcommerce.com/ 2. Click Register 3. Leave Email blank 4. Fill other fields correctly 5. Click Register |  |  | Passed
7 | Registration | Functional | Email Field Validation | Verify that the email field rejects inputs without “@” symbol | Display an error message “Wrong email” | Correctly displays “Wrong email” message | Email: soumik.com | 1. Go to https://demo.nopcommerce.com/ 2. Click Register 3. Enter soumik.com in Email field 4. Fill other fields correctly 5. Click Register |  |  | Passed
8 | Registration | Functional | Email Field Validation | Verify that the email field rejects incomplete domain | Display an error message “Wrong email” | Correctly displays “Wrong email” message | Email: soumik@com.c | 1. Go to https://demo.nopcommerce.com/ 2. Click Register 3. Enter soumik@com.c in Email field 4. Fill other fields correctly 5. Click Register |  |  | Passed
9 | Registration | Functional | Email Field Validation | Verify that the email field rejects fake domains | Display an error message “Wrong email” | Accepts soumik@com.cc and registration completes successfully | Email: soumik@com.cc | 1. Go to https://demo.nopcommerce.com/ 2. Click Register 3. Enter soumik@com.cc in Email field 4. Fill all fields correctly 5. Click Register | Click here to see the error. |  | Failed
10 | Registration | Functional | Password Field | Verify registration when Password field is empty | Error message “Password is required” should appear | Error message displayed: “Password is required” | Password: Blank; Confirm password: Blank | 1. Go to https://demo.nopcommerce.com/ 2. Click Register 3. Leave Password blank 4. Fill other fields correctly 5. Click Register |  |  | Passed
11 | Registration | Functional | Confirm Password Mismatch | Verify registration when Password and Confirm Password do not match | Error message “The password and confirmation password do not match.” should appear | Error message displayed | Password: soumik123; Confirm password: soumik1234 | 1. Go to https://demo.nopcommerce.com/ 2. Click Register 3. Enter mismatched passwords 4. Fill all other fields correctly 5. Click Register |  |  | Passed
12 | Registration | Functional | Password Field Validation | Verify that the system enforces password complexity (mixture of upper and lower case, digits, special characters) | Display an error message for weak passwords | System accepts weak passwords such as 111111 or aaaaaa and registers successfully | Password: 111111; Confirm password: 111111 | 1. Go to https://demo.nopcommerce.com/ 2. Click Register 3. Enter weak password 111111 4. Fill all fields correctly 5. Click Register | Click here to see the error. |  | Failed
13 | Registration | Functional | Company Name Field | Verify that the “Company Name” field can be left empty (optional) | Should allow registration without entering company name | Registers successfully without company name | Company Name: Blank | 1. Go to https://demo.nopcommerce.com/ 2. Click Register 3. Leave company name blank 4. Fill all other fields correctly 5. Click Register |  |  | Passed
14 | Registration | Functional | Newsletter Checkbox | Verify that user can select or deselect the Newsletter checkbox | Should allow both options (checked or unchecked) without blocking registration | Works correctly — registration successful in both cases | Newsletter: Checked / Unchecked | 1. Go to https://demo.nopcommerce.com/ 2. Click Register 3. Tick or untick the Newsletter checkbox 4. Fill all other fields correctly 5. Click Register |  |  | Passed
15 | Login | Functional | Email and Password field | Check login with both Email and Password blank | System should show message “Please enter your email” and not allow login | System displayed “Please enter your email” | Email: blank ; Password: blank | 1. Go to https://demo.nopcommerce.com/ 2. Click Log in 3. Leave both fields empty 4. Click Log in |  |  | Passed
16 | Login | Functional | Email Field | Check login with blank Email and valid Password | Should show “Please enter your email” message | System showed “Please enter your email” message | Email: blank | 1. Go to https://demo.nopcommerce.com/ 2. Click Log in 3. Leave email empty 4. Enter password 5. Click Log in |  |  | Passed
17 | Login | Functional | Password Field | Check login with valid Email and blank Password | Should show “The credentials provided are incorrect” | System showed error message "Login was unsuccessful and show .Please correct the errors and try again. The credentials provided are incorrect." | Password: blank | 1. Go to https://demo.nopcommerce.com/ 2. Click Log in 3. Enter email 4. Leave password empty 5. Click Log in |  |  | Passed
18 | Login | Functional | Unregistered Email | Check login with unregistered Email | Should show “No customer account found” | System showed error message "Login was unsuccessful. Please correct the errors and try again. No customer account found" | Email: unknown@gmail.com | 1. Go to https://demo.nopcommerce.com/ 2. Click Log in 3. Enter unregistered email 4. Enter password 5. Click Log in |  |  | Passed
19 | Login | Functional | Email Field Validation | Verify that the email field rejects inputs without “@” symbol | Should show an error message “Wrong email” | Correctly displays “Wrong email” message | Email: soumik.com | 1. Go to https://demo.nopcommerce.com/ 2. Click Log in 3. Enter invalid email format 4. Enter password 5. Click Log in |  |  | Passed
20 | Login | Functional | Email Field Validation | Verify that the email field rejects incomplete domain | Should show an error message “Wrong email” | Correctly displays “Wrong email” message | Email: soumik@com.c | 1. Go to https://demo.nopcommerce.com/ 2. Click Log in 3. Enter soumik@com.c 4. Enter password 5. Click Log in |  |  | Passed
21 | Login | Functional | Email Field Validation | Verify that the email field rejects fake domains | Should show an error message “Wrong email” | Accepts soumik@com.cc and logs in successfully if credentials match | Email: soumik@com.cc | 1. Go to https://demo.nopcommerce.com/ 2. Click Log in 3. Enter soumik@com.cc 4. Enter password 5. Click Log in | Click here to see the error. |  | Failed
22 | Login | Functional | Password Field | Verify login with registered Email and wrong Password | Should show “The credentials provided are incorrect” | Showed error message " Login was unsuccessful. Please correct the errors and try again. The credentials provided are incorrect." | Email: ss@gmail.com | 1. Go to https://demo.nopcommerce.com/ 2. Click Log in 3. Enter valid email 4. Enter wrong password 5. Click Log in |  |  | Passed
23 | Login | Functional | Valid Credentials | Check login with valid Email and Password | Should log in successfully and go to user dashboard | User redirected to dashboard successfully | Email: ss@gmail.com; Password:111111 | 1. Go to https://demo.nopcommerce.com/ 2. Click Log in 3. Enter correct email and password 4. Click Log in |  |  | Passed
24 | Password Recovery | Functional | Forgot Password | Verify Forgot Password with registered Email | Should show message “Email with instructions has been sent” | Correctly displays “Email with instructions has been sent” message | Email: ss@gmail.com | 1. Go to https://demo.nopcommerce.com/ 2. Click Log in 3. Click Forgot Password? 4. Enter registered email 5. Click Recover |  |  | Passed
25 | Password Recovery | Functional | Forgot Password | Check Forgot Password with unregistered Email | Should show message “Email not found” | Correctly displays “Email not found” message | Email: wow@gmail.com | 1. Go to https://demo.nopcommerce.com/ 2. Click Log in 3. Click Forgot Password? 4. Enter unregistered email 5. Click Recover |  |  | Passed

## Jira BugReportLink
Jira Bug Report Link
Click here to see the bug in JIRA.

## BugReport
Bug Report
SL: 1
Issue: Verify registration when First Name contains invalid characters.
Reproducing Steps: 1. Go to https://demo.nopcommerce.com/ 2.Click Register 3. Enter Soumik@123 in First Name field 4. Fill all other fields correctly 5. Click Register Expected Result: Show error message ‘Wrong first name format’ or first name field validation should prevent invalid characters Actual Result: Accepts invalid input and registration completes successfully.
Environment: Production.
Priority: High
Click here to see the error screenshot.
Bug Report
SL: 2
Issue: Verify registration when Last Name contains invalid characters.
Reproducing Steps: 1. Go to https://demo.nopcommerce.com/ 2. Click Register 3.Enter @@@ in Last Name field 4. Fill other fields correctly 5. Click Register Expected Result: Show error message ‘Wrong last name format’ or last name field validation should prevent invalid characters Actual Result: Accepts invalid input and registration completes successfully.
Environment: Production.
Priority: High
Click here to see the error screenshot.
Bug Report
SL: 3
Issue: Verify that the email field rejects fake domains.
Reproducing Steps: 1.Go to https://demo.nopcommerce.com/ 2. Click Register 3. Enter soumik@com.c in Email field 4. Fill other fields correctly 5. Click Register Expected Result: Display an error message ‘Wrong email’. Actual Result: Accepts soumik@com.cc and registration completes successfully.
Environment: Production.
Priority: Highest
Click here to see the error screenshot.
Bug Report
SL: 4
Issue: Verify that the system enforces password complexity (mixture of upper and lower case, digits, special characters).
Reproducing Steps: 1.Go to https://demo.nopcommerce.com/ 2. Click Register 3. Enter weak password 111111 4. Fill all fields correctly 5. Click Register Expected Result: Display an error message for weak passwords. Actual Result: System accepts weak passwords such as 111111 or aaaaaa and registers successfully.
Environment: Production.
Priority: Highest
Click here to see the error screenshot.
Bug Report
SL: 5
Issue: Verify that the email field rejects fake domains.
Reproducing Steps: 1.Go to https://demo.nopcommerce.com/ 2.Click Log in 3. Enter soumik@com.cc 4. Enter password 5. Click Log in Expected Result: Should show an error message 'Wrong email'. Actual Result: Accepts soumik@com.cc and logs in successfully if credentials match.
Environment: Production.
Priority: Highest
Click here to see the error screenshot.

## Test SummaryReport
Test Case Report | [6 empty] | Result :
Project Name | demo.nopcommerce.com
Module Name | Account. |  |  |  |  | Total No. | Status
Feature Name | Register Account & Account Login.
Test Case Version | 1 |  |  |  |  | 20 | PASS
Written By | A.B.M. Mahmudul Hasan(Soumik) |  |  |  |  | 5 | FAIL
Executed By | A.B.M. Mahmudul Hasan(Soumik) |  |  |  |  | 0 | Not Executed |  | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | xx |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 20 | 5 | 0 | 0 | 25 | Sum of PASS | Sum of FAIL | Sum of Not Executed | Sum of Out Of Scope
Grand Total | 20 | 5 | 0 | 0 | 25 | 20 | 5 | 0 | 0
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
No | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
NO | Usability Testing | Test application from user friendliness perspective.
NO | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
NO | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
NO | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Test Metrics
Test Metrics
SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (25/25)*100 | 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/25)*100 | 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (20/25)*100 | 80
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (5/25)*100 | 20
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/25)*100 | 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A | N/A
10 | Defect Age | Fixed date - Reported date | N/A | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A | N/A